## Detailed timeline
[Project name here]
[Organisation name] | [5 empty] | Resource days per work week available: | 3 | 60%
| Project Manager | [Name] |  | Total Available Calendar days: |  |  | 53
| Project Start Date | 2019-12-15 |  | Required Resource days: |  |  | 30 | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30
| Project End Date | 2020-02-06 |  | Available Resource days: |  |  | 31.8 |  |  |  | 2019-12-16 | [6 empty] | 2019-12-23 | [6 empty] | 2019-12-30 | [6 empty] | 2020-01-06 | [6 empty] | 2020-01-13 | [6 empty] | 2020-01-20 | [6 empty] | 2020-01-27 | [6 empty] | 2020-02-03 | [6 empty] | 2020-02-10 | [6 empty] | 2020-02-17 | [6 empty] | 2020-02-24 | [6 empty] | 2020-03-02 | [6 empty] | 2020-03-09 | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29 | [6 empty] | 2020-07-06
 | time axis 2019-12-16 to 2020-07-12
WBS | WORKSTREAM / TASK | LEAD | DEPENDANCY | START DATE | CALENDAR DAYS REQUIRED | RESOURCE DAYS REQUIRED | END DATE | CALENDAR DAYS AVAILABLE | % COMPLETE | RESOURCE DAYS AVAILABLE | time axis 2019-12-16 to 2020-07-12
1 | [Example workstream 1] | - | - | 2019-12-15 | 37 | 13 | 2020-01-21 | 37 | 59% | 16.2
1.1 | [Activity 1] | AA |  | 2019-12-15 | 3 | 1 | 2019-12-18 | 3 | 100% | 1.8
1.2 | [Activity 2] | AA |  | 2019-12-19 | 5 | 2 | 2019-12-26 | 7 | 95% | 3.6
1.3 | [Activity 3] | AA |  | 2019-12-27 | 2 | 3 | 2019-12-31 | 4 | 80% | 1.8
1.4 | [Activity 4] | AA |  | 2020-01-01 | 1 | 2 | 2020-01-02 | 1 | 10% | 1.2
1.5 | [Activity 5] | AA |  | 2020-01-03 | 12 | 5 | 2020-01-21 | 18 | 10% | 7.8
2 | [Example workstream 2] |  |  | 2020-01-13 | 24 | 9 | 2020-02-06 | 24 | 0% | 11.4
2.1 | [Activity 1] | AA |  | 2020-01-13 | 3 | 2 | 2020-01-16 | 3 | 0% | 2.4
2.2 | [Activity 2] | AA |  | 2020-01-17 | 2 | 1 | 2020-01-21 | 4 | 0% | 1.8
2.3 | [Activity 3] | AA |  | 2020-01-22 | 5 | 3 | 2020-01-29 | 7 | 0% | 3.6
2.4 | [Activity 4] | AA |  | 2020-01-30 | 3 | 2 | 2020-02-04 | 5 | 0% | 2.4
2.5 | [Activity 5] | AA |  | 2020-02-05 | 1 | 1 | 2020-02-06 | 1 | 0% | 1.2
3 | [Example workstream 3] |  |  | 2020-02-05 | 23 | 8 | 2020-02-28 | 23 | 0% | 10.8
3.1 | [Activity 1] | AA |  | 2020-02-05 | 2 | 1 | 2020-02-07 | 2 | 0% | 1.8
3.2 | [Activity 2] | AA |  | 2020-02-10 | 2 | 1 | 2020-02-12 | 2 | 0% | 1.8
3.3 | [Activity 3] | AA |  | 2020-02-13 | 4 | 4 | 2020-02-19 | 6 | 0% | 3
3.4 | [Activity 4] | AA |  | 2020-02-20 | 2 | 1 | 2020-02-24 | 4 | 0% | 1.8
3.5 | [Activity 5] | AA |  | 2020-02-25 | 3 | 1 | 2020-02-28 | 3 | 0% | 2.4
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [Workstream title template] | - | - | 0 | 3 | 0 | 1900-01-02 | 3 | 0% | #VALUE!
1.1 | [Activity template] | AA |  | 0 | 0 | 0 | 0 | 0 | 0% | #VALUE!
1.2 | [Activity 2] | AA |  | 1900-01-01 | 0 | 0 | 1900-01-01 | 0 | 0% | 0.6
1.3 | [Activity 3] | AA |  | 1900-01-02 | 0 | 0 | 1900-01-02 | 0 | 0% | 0.6
Note on H2: In every 5 calendar days, how may resource days do you have? If you have 1 person working full time on a project, you can input 5 resource days for a 5 day week. If you have 1 person working half their time, you can input 2.5 working days per week. If you have 2 people working full time, you have 10 resource days in a week
Note on H3: Will automatically calculate based on difference between project start and end dates
Note on H4: Automtically calculated depending on the number of resource days required per workstream
Note on J4: Use this to quickly jump to the desired project week
Note on C5: Will automatically fill based on maximum dates provided in timeline below
Note on H5: You can use this if you have more or less than one person/resource working on the project. It allows you to see how many actual resource days you have available for the whole project. If the number is smaller than the required resource days, the box will turn RED, indicating you don't have enough personel resources to deliver the project
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor task. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: The number of days this task is this expected to take take in total, inlcuding waiting time
Note on G7: The amount of condensed worktime (in days) needed to deliver the task/workstream
Note on H7: End Date: Calculated based on the Start Date and the Calendar Days columns.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K7: Work Days Automatically calculates the number of resource days you have available to deliver the task based on the Counts the number of work days, excluding the weekends (Saturday and Sunday). T
Note on D9: Does this task rely on another task to finish first? Copy and past the grid reference for the dependency here
Note on E9: When is this task expected to start? You can manually input it here, or copy and paste the link to the end date of a dependency task, or use a formula like =workday(link,1) to say 'starts the workday after another task finishes'
Note on F9: How many calendar days should this task take? How many calendar days do you feel it should reasobly take. Taking into account any waiting periods. For example, seeking approval can take several days or weeks of waiting
Note on G9: How many actual days of work will this take?
Note on H9: When is this task expected to finish? You can set this manually, or you can use the formula (=Stard Date + Working Days required) to calculate when the should be completed
Note on I9: How many calendar days do you have available to get this task done? Automatically calculated based on start and completion date for task. Useful if different from the resource days required.
Note on J9: What % is this task complete? Based on intuition / gut feeling
Note on K9: How many resource days do you have in that calendar period? Will automatically calculate how many working resource days you have available in the calendar period for the task. If the value is less than the number in the resource days required box, this box will turn RED, indicating you may not have enough resources available in the available timeperiod to deliver the task
Note on D15: Does this task rely on another task to finish first? Copy and past the grid reference for the dependency here
Note on E15: When is this task expected to start? You can manually input it here, or copy and paste the link to the end date of a dependency task, or use a formula like =workday(link,1) to say 'starts the workday after another task finishes'
Note on F15: How many calendar days should this task take? How many calendar days do you feel it should reasobly take. Taking into account any waiting periods. For example, seeking approval can take several days or weeks of waiting
Note on G15: How many actual days of work will this take?
Note on H15: When is this task expected to finish? You can set this manually, or you can use the formula (=Stard Date + Working Days required) to calculate when the should be completed
Note on I15: How many calendar days do you have available to get this task done? Automatically calculated based on start and completion date for task. Useful if different from the resource days required.
Note on J15: What % is this task complete? Based on intuition / gut feeling
Note on K15: How many resource days do you have in that calendar period? Will automatically calculate how many working resource days you have available in the calendar period for the task. If the value is less than the number in the resource days required box, this box will turn RED, indicating you may not have enough resources available in the available timeperiod to deliver the task
Note on D21: Does this task rely on another task to finish first? Copy and past the grid reference for the dependency here
Note on E21: When is this task expected to start? You can manually input it here, or copy and paste the link to the end date of a dependency task, or use a formula like =workday(link,1) to say 'starts the workday after another task finishes'
Note on F21: How many calendar days should this task take? How many calendar days do you feel it should reasobly take. Taking into account any waiting periods. For example, seeking approval can take several days or weeks of waiting
Note on G21: How many actual days of work will this take?
Note on H21: When is this task expected to finish? You can set this manually, or you can use the formula (=Stard Date + Working Days required) to calculate when the should be completed
Note on I21: How many calendar days do you have available to get this task done? Automatically calculated based on start and completion date for task. Useful if different from the resource days required.
Note on J21: What % is this task complete? Based on intuition / gut feeling
Note on K21: How many resource days do you have in that calendar period? Will automatically calculate how many working resource days you have available in the calendar period for the task. If the value is less than the number in the resource days required box, this box will turn RED, indicating you may not have enough resources available in the available timeperiod to deliver the task
Note on D32: Does this task rely on another task to finish first? Copy and past the grid reference for the dependency here
Note on E32: When is this task expected to start? You can manually input it here, or copy and paste the link to the end date of a dependency task, or use a formula like =workday(link,1) to say 'starts the workday after another task finishes'
Note on F32: How many calendar days should this task take? How many calendar days do you feel it should reasobly take. Taking into account any waiting periods. For example, seeking approval can take several days or weeks of waiting
Note on G32: How many actual days of work will this take?
Note on H32: When is this task expected to finish? You can set this manually, or you can use the formula (=Stard Date + Working Days required) to calculate when the should be completed
Note on I32: How many calendar days do you have available to get this task done? Automatically calculated based on start and completion date for task. Useful if different from the resource days required.
Note on J32: What % is this task complete? Based on intuition / gut feeling
Note on K32: How many resource days do you have in that calendar period? Will automatically calculate how many working resource days you have available in the calendar period for the task. If the value is less than the number in the resource days required box, this box will turn RED, indicating you may not have enough resources available in the available timeperiod to deliver the task

## Gantt Guidance
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
• Define the task start date and duration (days) by editing the light green cells.
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color.
FAQs
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
Note on C5: This is an example comment.